## Backlog
Id. | Importance | Title | User Story | Acceptance Criteria | Estimate | Sprint
1 | 30 | Monitor and manage permissions | As an Administrator, I aim to control the permissions for performing actions in the website and monitor site visits | Assign appropriate access control to users, visitors, and employees as well as create an access log to record access attempts and user info | 2-3 weeks | Q2 - Sprint III
2 | 30 | Create, edit, delete contents | As an Administrator, I want to be able to add, update, and remove the contents of the main website | Add new articles with relevant information such as title, body text, author, and publication date and also update it from time to time. The contents should be visible to users, visitors and employees and reflect the changes made if ever the administrator edited an article. Lastly, authorized personnel should be allowed to delete content, which would result in to permanent removal from the website | 2 weeks | Q3 - Sprint I
3 | 30 | Add/Update Security Measures | As an Administrator, I want to protect the website against vulnerabilities, fix bugs, and safeguard the users’ data, the company’s reputation, and the website itself. | Regularly conduct vulnerability assessments and implement appropriate security measures to mitigate potential risks and identify and resolve any reported bugs. Also, secure data storage methods, create backups of the website and user data regularly to prevent data loss and ensure security of assets. Importantly, regularly monitoring and updating the applied security measures to stay ahead of emerging threats and vulnerabilities | 1 month for the first implementation then afterwards, it will be regualrly checked and updated by the developers | Q2 - Sprint IV so on (continuous)
4 | 20 | View website analytics | As an Administrator, I aim to track the performance of the website , user behavior, and make informed decisions for the improvement of the website | Generate a report analytics such as session duration, successful transactions, themes, and even response time of the server and DBMS to track the performance of the website, understand user behavior patterns, and make informed decisions for the improvement of the website | 1-2 weeks for setting up analytical tools and first report | (not included in product roadmap eotteoke)
5 | 30 | Save backups of the website’s data | As an Administrator, I want to ensure data integrity, prevent data loss and recover if potential issues arise | Validation rules should be applied to avoid data corruption or tampering of unauthorized personnel. Moreover, the stored backup should be separately stored outside the website and should be secured. The data recovery process should also be updated regularly to ensure successful data restoration when needed. | 1 month for the first implementation then afterwards, it will be regualrly checkd and updated by the developers | Q2 - Sprint IV so on (continuous)
6 | 10 | Improve Company Branding | As an Administrator, I want to configure Search Engine Optimization (SEO) and Website Branding | To maintain consistent brand and improve website visibility, necessary tools and settings to configure SEO should be accessible as well as website keywords should be implemented in search engines. Additionally, the visual impact, layout, and logo of the website should reflect the company's branding
7 | 30 | Access document in one place | As an Employee, I want to be able to access my documents in one place so that I can work on orders more efficiently | The employee should have a centralized document repository within the system where they can access their documents. Sorting and filtering criteria systems should be in place for a clear and organized view of all the employee's documents. There should also be a search option that can help in presenting relevant documents through the order number, client name, or keywords. The system should also display relevant information about each document such as the order number, client associated, creation and modification date, document type and document status.
8 | 30 | Client authentication for documents | As an Employee, I want to be able to restrict access to documents so only the clients involved and I will be able to access them privately. | Setting authentication measures by restricting client access to documents should be implemented to protect the privacy of the client's sensitive information. Only authenticated users can view and interact with the content using the client access password given to them by their respective employee contact. Once the employee deems the document to be ready for viewing, he/she will send the password through email.
9 | 20 | Appointment booking system | As a client, I want to be able to schedule an appointment through the system so that I can easily book a meeting and prepare the files I need for the appointment. | The appointment booking system is accessible and prominently displayed within its section on the webpage so clients are able to book an appointment easily. Upon confirmation within the website, an auto-generated email will be sent to the client's contact email with the necessary details regarding the schedule. Finally, a checklist of required documents are provided in the appointment page at the client's dashboard so they will be able to prepare the files beforehand. A list of Frequently Asked Questions (FAQs) and tips are also provided to further assist the customer.
10 | 20 | Order progress tracking | As a client, I want to be able to see the progress of my order so that I am up to date with the development of my document and give feedback for needed changes in the order. | The client should be able to access a dedicated section or page within the system where they can view the progress of their order. It should display relevant information about the order's status, such as the current stage and a summary of the recent changes or the recent completed milestone. It should be updated in real-time or at regular intervals. There should also be a space where customers are able to provide feedback or request for changes regarding the order for easy access. A quick glance of the order progress should also be present in a section of the main client dashboard which they can click to expand and take them to the dedicated progress page.
11 | 10 | Updated Contact information | As a client, I want to be able to update my contact details easily so that the company are informed to where my preferred contact medium is and reach me immediately. | Clients should be able to modify their contact information such as phone number, email address, and mailing address in their profile settings section available once they log into the system. Validation of the entered contact information should be made to ensure the it follows the format and accuracy of the details. The client should receive a confirmation message/email to finalize the changes for security purposes.
12 | 20 | Document filter system | As a client, I want to be able to filter documents based on my preference so that I can easily browse and access my files depending on my needs. | Completed documents is provided to the authorized account only and are located in a separate page from ongoing orders. Both categories have a sorting and filtering system where clients are able to organize according to date, date range, document type, and other options. The document entries also contain a brief summarized report that includes the case description, assigned lawyer, and status so customers are able to easily identify the files.
13 | 30 | Client dashboard | As a client, I want to be able to view a personal dashboard so that I can easily see the progress of my ongoing orders, recent completed orders and important dates and information in a glance. | A client dashboard is available once the customer logs into the system. There, they will be able to see updates on their active order/s, their recently completed transactions as well as appointment dates if available. A calendar will also be provided where clients are able to see their respective schedules with the date, time, and details provided for them to track important dates and information.
14 | 20 | Customer feedback and review input | As a client, I want to be able to leave a review regarding my transactions so that other users are able to be informed of the quality of the service I was provided. | The client should be able to easily access the section where they are able to leave a review regarding their transactions on the website. The review submission process should require the client to provide the required information such as their name or initials. The system should ensure the privacy of the customer's personal information by letting them choose between displaying their name or initials with the review. The system should validate to ensure its completeness, integrity and authenticity to prevent spam or fraudulent reviews. The form should allow the client to provide detailed feedback regarding the service quality, customer support, timeliness and overall satisfaction. The system should be able to handle the amount of reviews without affecting the performance of the website. The feedback should be updated and displayed real-time on the service page and the customer testament page.
15 | 30 | Account Creation | As a visitor, I want to be able to create and log into my account so that I can start availing the services I need. | The visitor should be able to clearly and easily access the option to create an account on the system. Information validation should then be made to ensure the accuracy and completeness of the required fields such as the name, contact details, and password. After the account creation, the visitor should receive an email confirmation containing a verification link or code to activate their account.
16 | 10 | Service list webpage | As a visitor, I want to be able to see the list of services that the company offers so that I can use it as a reference for my orders. | The list of services should be displayed in a dedicated webpage within the website that is clear and easily accessible by visitors. Each service should be presented in a well-structured and organized manner by having a descriptive tite or name and a brief description or overview of the service provided while users navigate the page. If applicable, it should include the pricing information or cost estimates, providing transparency to the visitor.
17 | 10 | Employee and partners page | As a visitor, I want to be able to access a directory that lists the company's staff members and view the partners affliated with the company so that I can see their areas of expertise and build trust on the company. | There should be a separate webpage for staff and partners directory that visitors are able to clearly see and easily access. The directory should display a list of staff members along with their basic information such as their names, job titles, and display pictures. Upon selecting a staff member, their profile should appear including a brief description of their expertise, highlighting their key skills and areas of knowledge. For easy navigation, a search or filter functionality should be provided that allows the visitor to search for staff members based on category types. The partners section should provide a list of partner names and their respective logos or branding, if applicable.
18 | 20 | Viewing customer reviews and testaments | As a visitor, I want to be able to see previous customers' reviews and feedback so that I am able to view how previous transactions went and use it as basis whether to avail the company's services. | Customer reviews and testaments should be seen in a separate section as well as under the expanded profile of each service. Each review should include the customer's name or initials, to preserve anonimity, along with their rating or qualitative feedback. The feedback should cover various aspects of the company's services such as quality, customer support, timeliness and overall satisfaction. The reviews and feedback section should provide a filter functionality so visitors are able to search for specific categories of reviews. The entries should be displayed in chronological or relevance-based order depending on the user's choice.

## Backlog filled
Id. | Importance | Title | User Story | Acceptance Criteria | Estimate
2 | 10 | Sorting by likely matches | As a bird finder, I want to see a list of matching birds sorted by likely matches so that I can learn more about bird watching.
1 | 20 |  | As a bird finder, I want to see a list of matching birds on my smartphone so I can learn more about birds when I’m away from my house.
3 | 30 | Using GPS to find likely matches | As a bird finder, I want to see a list of matching birds based on my uploaded GPS coordinates so that I can learn more about bird watching.